## Overview
Project Information
PMHub.ru
Parameter | Value
Project | Horizon ERP Implementation
Project Manager | Anna
Date | 2026-10-24
Assign one accountable owner to each critical dependency.

## Dependencies
Dependency Control
PMHub.ru
ID | Upstream Deliverable | Dependent Task | Owner | Team | Impact | Required By | Response Plan | Next Review | Status
DEP-01 | Orders API v2 | Mobile Client Integration | Alex | Backend | High | 2026-11-02 | Review contract and test environment | 2026-10-29 | In Progress
DEP-02 | Design Approval | UI Development | Maria | Design | Medium | 2026-11-07 | Run design review | 2026-11-01 | Open
DEP-03 | Test Environment Access | Integration Tests | Ivan | Platform | Low | 2026-10-29 | Grant access to testers | 2026-10-27 | Resolved

## Dashboard
Dependency Status
PMHub.ru
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
3 |  | 3
Distribution by category
Open | 1
In Progress | 1
Resolved | 1