## Overview
Project Details
PMHub.ru
Parameter | Value
Project | Horizon ERP Implementation
Project Manager | Anna Kozlova
Date | 2026-10-24
Update the register first, then review calculated values and the summary.

## Hiring Plan
Hiring and Capacity Load Plan
PMHub.ru
ID | Role | Team | Current FTE | Required FTE | Confirmed Hires | Hiring Gap FTE | Start Date | Status
HL-01 | Backend Engineer | Platform | 2 | 5 | 1 | 2 | 2026-11-16 | Recruiting
HL-02 | Business Analyst | ERP | 1 | 2 | 1 | 0 | 2026-12-01 | Filled
HL-03 | QA Engineer | Quality Assurance | 2 | 4 | 0 | 2 | 2026-12-15 | Planned

## Dashboard
Status Summary
PMHub.ru
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
3 |  | 3
Distribution by category
Planned | 1
Recruiting | 1
Filled | 1