## Overview
Project Information ¦ v2
PMHub.me ¦ v2
Parameter | Value
Project | Horizon ERP Implementation
Project Manager | Anna
Date | 2026-10-24
Monetary unit (currency and scale) | USD
Negative remaining budget indicates a forecast overrun.
Set a monetary unit in the project overview and use it consistently for all amount fields. Do not mix currencies or scales.

## Budget
Project Budget ¦ v2
PMHub.me ¦ v2
ID | WBS Element | Cost Category | Owner | Budget | Actual | Committed | Forecast | Budget Remaining | Status
B-01 | 1.1 | Development | Oleg | 3200000 | 1100000 | 1600000 | 2700000 | 500000 | Confirmed
B-02 | 1.2 | Licenses | Daria | 850000 | 600000 | 300000 | 900000 | -50000 | Overrun Risk
B-03 | 1.3 | Training | Inna | 600000 | 100000 | 250000 | 350000 | 250000 | Draft

## Dashboard
Budget Item Status ¦ v2
PMHub.me ¦ v2
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
3 |  | 3
Distribution by category
Draft | 1
Confirmed | 1
Overrun Risk | 1