## Project Overview
Project Overview
PMHub.ru
Parameter | Value
Project | Regional CRM Rollout
Project Manager | Anna Kozlova
Sponsor | Operations Director
Last Updated | 2026-10-22
Keep risks, assumptions, issues and dependencies on separate worksheets.
The Dashboard uses COUNTIF formulas for risk statuses after Excel recalculates the workbook.
Dates and scores are entered manually. The file does not automatically forecast risk likelihood.
Worksheet navigation
Risks
Assumptions
Issues
Dependencies
Dashboard

## Risks
Risk Register
PMHub.ru
ID | Description | Probability | Impact | Owner | Response Plan | Review Date | Status | Early Warning Indicator
R-01 | Customer data migration delay | High | High | IT Lead | Run trial migration and data reconciliation | 2026-11-02 | In Progress | Failed control load
R-02 | Insufficient staff training | Medium | High | HR Business Partner | Pilot training across two branches | 2026-11-06 | Open | Training completion below target

## Assumptions
Assumptions Register
PMHub.ru
ID | Assumption | Validation Method | Owner | Review Date | Status | Consequence
A-01 | Customer data is ready for trial migration | Check export in test environment | Data Lead | 2026-10-29 | Open | UAT start delayed

## Issues
Issue Log
PMHub.ru
ID | Issue | Impact | Owner | Next Action | Review Date | Status | Decision
I-01 | CRM API access not approved | High | Technical Lead | Agree service account list | 2026-10-27 | In Progress | Escalate to architecture committee

## Dependencies
Dependency Log
PMHub.ru
ID | Dependency | Predecessor | Owner | Review Date | Status | Blocking | Next Action
D-01 | CRM API availability | Integration Team | Integration Lead | 2026-10-30 | On Track | Test environment | Run end-to-end request

## Dashboard
Risk Status Summary
PMHub.ru
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
2 |  | 2
Distribution by category
Open | 1
In Progress | 1
Closed | 0