## Overview
Project Details
PMHub.ru
Parameter | Value
Project | Horizon ERP Implementation
Project Manager | Anna Kozlova
Date | 2026-10-24
Update the register first, then review calculated values and the summary.

## Hour Allocation
Project Resource Allocation
PMHub.ru
ID | Person | Role | Team | Available Hours | Allocated Hours | Utilization | Remaining Hours | Period | Status
A-01 | Ivan Petrov | Backend Engineer | Platform | 160 | 180 | 112.5% | -20 | November 2026 | Overallocated
A-02 | Maria Volkova | Analyst | ERP | 160 | 152 | 95% | 8 | November 2026 | Balanced
A-03 | Oleg Pavlov | QA | Testing | 160 | 90 | 56.25% | 70 | November 2026 | Underallocated

## Dashboard
Status Summary
PMHub.ru
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
3 |  | 3
Distribution by category
Balanced | 1
Overallocated | 1
Underallocated | 1