## Overview
Project Details
PMHub.ru
Parameter | Value
Project | Horizon ERP Implementation
Project Manager | Anna Kozlova
Date | 2026-10-24
Update the register first, then review calculated values and the summary.

## Risk Scoring
Project Risk Scoring Model
PMHub.ru
ID | Risk Description | Likelihood (1–5) | Impact (1–5) | Score | Rating | Owner | Status | Mitigation
R-01 | Data Migration Delay | 4 | 5 | 20 | Critical | Anna | Identified | Trial migration
R-02 | Contractor Cost Increase | 3 | 4 | 12 | High | Paul | In Progress | Fix contract terms
R-03 | Slow User Adoption | 2 | 2 | 4 | Low | Lena | Closed | User onboarding

## Dashboard
Status Summary
PMHub.ru
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
3 |  | 3
Distribution by category
Identified | 1
In Progress | 1
Closed | 1